## Budget_Application_Form
Budget Application Form

Send this form to budget@typo3.org by latest at the stated deadline below. You will receive an automatic answer from our ticket system, confirming that your budget application was received. All inquiries regarding this budget form should be made to the Board by email. We are happy to help and guide you by setting up your budget application. General information about the budget process can be found here.

I General Information

Budget Period	01.01.2021 – 31.12.2021
Deadline	05.02.2021

Your Project
Project Name	Automatically capture screenshots for the official documentation
Description	Have a script that automatically captures all reproducable (TYPO3 Backend or Frontend), non-edited (arrows, boxes, numbers) screenshots. Have a clear steps of reproduction for screenshots that have to be reproduced manually. Document the screenshot tool. Have clear steps for ppl who want to add new screenshots to the official documentation. Make sure the tool either runs locally on Linux, Max and Windows or on the Server like bamboo such that it can be used by a large number of contributors.

Budget Owner
Name	Lina Wolf
E-Mail	112@linawolf.de
Phone Number	"+49 176 255 77 587"
Slack Username	Lina Wolf
typo3.org Username	linawolf

Mentor	If you have never been a budget owner, you need to have an experienced budget owner as mentor. Name your mentor and make him co-leader of your Forge Project.

Name	Martin Bless
E-Mail	[mentor's e-mail address]

Your Team
Total Members	4 for now
Members' Names	Lina Wolf, Martin Bless, Alexander Nitsche, Thomas Anders / Naderio

II Milestones

Title	Deliverables
Analyzing Tools for taking automated Screenshot	31.03.2021, Have a tool that can take Screenshots from different part of the backend
Make an Overview of all needed Screenshots in all needed manuals	31.6.2021, Have a list of all currently used screenshots in the official documentation and how to reproduce them
Write a special automated tools for all automatically creatable Screenshots and document it	30.09.2021, Have a tool that can automatically update Screenshots from one manual
Generalize Automated tool and create all screenshots. document it	15.12.2021, All Screenshots in all affected manuals have been exchanged with Version 11 and style guide

If you plan to use agile project management please contact the Board beforehand.

III Calculation

Categories
EN: enabling costs (travel, hotel, infrastructure, food and bevarges during sprints, Tickets for events, …)
WT: worktime costs (please note, that we prefer funding projects, that use a maximum of 50% paid working time)
AC: acknowledgements costs (acknowledgement of a sum, which is not in a direct relation to working hours or items like amazon voucher. If money is acknownledged, it should not higher in sum as the same result in woring hours)
					Total Costs:	7.500,00 €

Milestone #		Category	Item	Units	Cost per Unit (€)	Total per Item	Total per Milestone
1 – Describe your Milestone / Quarter here: Analyzing Tools for taking automated Screenshot		AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
		EN	Food for Online Code Sprint	6	30	180,00 €
		WT	Acceptance Testing like in the core extension, Analyse	5	55	275,00 €
		WT	Pupeteer, analyse	12	55	660,00 €
		WT	Other tools?	5	55	275,00 €
		AC	Aknowledgement for Helpers	6	50	300,00 €
					1.990,00 €
2 – Describe your Milestone / Quarter here: Have a list of all currently used screenshots in the official documentation and how to reproduce them		AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
		EN	Food for Online Code Sprint	5	30	150,00 €
		WT	Decide which manuals to be supported	2	55	110,00 €
		WT	TYPO3 Explained, Screenshot reproduction	6	55	330,00 €
		WT	References Screenshot reproduction	6	55	330,00 €
		WT	Tutorials & Guides Screenshot reproduction	6	55	330,00 €
		AC	Aknowledgement for Helpers	5	50	250,00 €	1.800,00 €
2 – Describe your Milestone / Quarter here: Screenshot tool for TCA Reference		AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
		EN	Food for Online Code Sprint	6	30	180,00 €
		WT	Writing the tool	15	55	825,00 €
		AC	Aknowledgement for Helpers	6	50	300,00 €
					0,00 €
					0,00 €
					1.605,00 €
2 – Describe your Milestone / Quarter here: Screenshot tool for all official Manuals		AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
		EN	Food for Online Code Sprint	6	30	180,00 €
		WT	Writing the tool	15	55	825,00 €
		WT	Documenting the tool	10	55	550,00 €
		AC	Aknowledgement for Helpers	5	50	250,00 €
					0,00 €
					2.105,00 €