## Budget_Application_Form
Budget Application „T3Docs SIG Screenshots“

I General Information

Budget Period		01.01.2021 – 31.12.2021
Deadline		05.02.2021

Project
Project Name		Automatically capture screenshots for the official documentation
Description		Have a script that automatically captures all reproducable (TYPO3 Backend or Frontend), non-edited (arrows, boxes, numbers) screenshots. Have a clear steps of reproduction for screenshots that have to be reproduced manually. Document the screenshot tool. Have clear steps for ppl who want to add new screenshots to the official documentation. Make sure the tool either runs locally on Linux, Max and Windows or on the Server like bamboo such that it can be used by a large number of contributors.

Budget Owner
Name		Lina Wolf
E-Mail		112@linawolf.de, lina.wolf@typo3.org
Phone Number		+49 176 255 77 587
Slack Username		Lina Wolf
typo3.org Username		linawolf

Mentor

Name		Martin Bless
E-Mail		martin.bless@typo3.org

Your Team
Total Members		4 for now
Members' Names		Lina Wolf, Martin Bless, Alexander Nitsche, Thomas Anders / Naderio

II Milestones

Title		Deliverables

1. Generalize automated tool, create all simple screenshots, document that.		30.06.2021 All simple Screenshots (without annotations) in all affected manuals have been exchanged with Version 11
2. Write actions to automatically annotate screenshots with arrows, labels and boxes. Make them nice		30.09.2021 All annotated screenshots in all affected manuals have been replaced
3. Automatically run tool in Docker, make a proof of concept about how to replace screens in extensions		15.12.2021 Screenshot tools runs automatically with reports. Screens in a system extension have been replaced

III Calculation

Categories: EN (enabling), WT (worktime), AC (acknowledgements)					Budget total:	30.000,00

Milestone (M.)	Cat.	Item	Units	à €	Total Item	Total M.
1. Generalize automated tool, create all simple screenshots, document that.	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
	EN	Food for Online Code Sprint	6	30	180,00 €
	WT	Replace a total of 400 screenshots in 11 manuals (2/h)	200	55	11.000,00 €
	WT	Update script for further screenshot types	40	55	2.200,00 €
	WT	Introduce additional actions for special cases	24	55	1.320,00 €
	AC	Aknowledgement for Helpers	5	50	250,00 €
					15.250,00
2. Write actions to automatically annotate screenshots with arrows,	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
labels and boxes. Make them nice	EN	Food for Online Code Sprint	6	30	180,00 €
	WT	Replace a total of 100 screenshots with annotations in 11 manuals (1/h)	100	55	5.500,00 €
	WT	Introduce actions to annotate screenshots	24	55	1.320,00 €
	WT	Improve layout of annotations and screenshots	40	55	2.200,00 €
	AC	Aknowledgement for Helpers	5	50	250,00 €	9.750,00
3. Automatically run tool in Docker, make a proof of concept about	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
how to replace screens in extensions	EN	Food for Online Code Sprint	9	30	270,00 €
	WT	Automatically run tool on docker with reports ec	40	55	2.200,00 €
	WT	Proof of concept with one extension	16	55	880,00 €
	WT	Support system extension editors to use the tool	20	55	1.100,00 €
	AC	Aknowledgement for Helpers	5	50	250,00 €
					5.000,00