## Budget_Application_Form
Budget Application „T3Docs SIG Screenshots“

I General Information

Budget Period		01.01.2021 – 31.12.2021
Deadline		05.02.2021

Project
Project Name		Automatically capture screenshots for the official documentation
Description		Have a script that automatically captures all reproducable (TYPO3 Backend or Frontend), non-edited (arrows, boxes, numbers) screenshots. Have a clear steps of reproduction for screenshots that have to be reproduced manually. Document the screenshot tool. Have clear steps for ppl who want to add new screenshots to the official documentation. Make sure the tool either runs locally on Linux, Max and Windows or on the Server like bamboo such that it can be used by a large number of contributors.

Budget Owner
Name		Lina Wolf
E-Mail		112@linawolf.de, lina.wolf@typo3.org
Phone Number		+49 176 255 77 587
Slack Username		Lina Wolf
typo3.org Username		linawolf

Mentor

Name		Martin Bless
E-Mail		martin.bless@typo3.org

Your Team
Total Members		4 for now
Members' Names		Lina Wolf, Martin Bless, Alexander Nitsche, Thomas Anders / Naderio

II Milestones

Title		Deliverables
1. Develop tooling for automated screenshots		31.03.2021 Have one or more workflows developed
2. Make an overview of all needed screenshots in all relevant manuals		30.06.2021 Have a list of all currently used screenshots in the official documentation and how to reproduce them
3. Write a special automated tools for all automatically creatable / screenshots and document that		30.09.2021 Have a tool that can automatically update Screenshots from one manual
4. Generalize automated tool, create all screenshots, document that.		15.12.2021 All Screenshots in all affected manuals have been exchanged with Version 11 and style guide

III Calculation

Categories: EN (enabling), WT (worktime), AC (acknowledgements)					Budget total:	7.500,00

Milestone (M.)	Cat.	Item	Units	à €	Total Item	Total M.
1. Develop tooling for automated screenshots	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
	EN	Food for Online Code Sprint	6	30	180,00 €
	WT	Acceptance Testing like in the core extension, Analyse	5	55	275,00 €
	WT	Pupeteer, analyse	12	55	660,00 €
	WT	Other tools?	5	55	275,00 €
	AC	Aknowledgement for Helpers	6	50	300,00 €
					1.990,00
2. Have a list of all currently used screenshots in the official / documentation and how to reproduce them	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
	EN	Food for Online Code Sprint	5	30	150,00 €
	WT	Decide which manuals to be supported	2	55	110,00 €
	WT	TYPO3 Explained, Screenshot reproduction	6	55	330,00 €
	WT	References Screenshot reproduction	6	55	330,00 €
	WT	Tutorials & Guides Screenshot reproduction	6	55	330,00 €
	AC	Aknowledgement for Helpers	5	50	250,00 €	1.800,00
3. Screenshot tool for TCA Reference	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
	EN	Food for Online Code Sprint	6	30	180,00 €
	WT	Writing the tool	15	55	825,00 €
	AC	Aknowledgement for Helpers	6	50	300,00 €
					0,00 €
					0,00 €
					1.605,00
4. Generalize automated tool, create all screenshots, document that.	AC	Aknowledgement for ca. 4h / week team mgm. per month	3	100	300,00 €
	EN	Food for Online Code Sprint	6	30	180,00 €
	WT	Writing the tool	15	55	825,00 €
	WT	Documenting the tool	10	55	550,00 €
	AC	Aknowledgement for Helpers	5	50	250,00 €
					0,00 €
					2.105,00